## Revised Eventflow
EVENT FLOW
Date | Event/ Activity | Venue | Start time | End time | Music/ Accessory | Remarks
26th October- DAY 0
Team 1 from MEW arrives in Udaipur
| Janki's family- Mumbai- Udaipur |  | 12:15 | 13:45
| Rahul & family (parents & sister)- Delhi-Udaipur |  | 12:40
| Transfer to Nathdwara ( 13 pax- Janki's family) |  | 15:00 | 16:00 |  | *4-5 Innovas to be arranged
| Darshan at Nathdwara |  | 16:00 | 17:00
| Transfer to TRIDENT (18 pax- Janki's family) |  | 17:00 | 18:00
| Check-in and Unpack | Trident | 18:30 | 19:30
Handover plastic glasses to hotel for pool party
Tempo with family bags to arrive at Leela
27th October- DAY 1
Team 2 from MEW arrives in Udaipur
Transfer of few guest from Airport to Nathdwara (Janki's family)
| Darshan at Nathdwara | Nathdwara
| Transfer from Trident to Leela (Janki's family) |  | 13:00 | 14:00
Local Pandit to arrive for engagement
Small thali with sweets by JMB to be ready for enegagement
| Engagement at Janki's room | Royal Suite | 14:30 | 15:30 |  | * 1 local pandit *2 kgs sweets
| Madha Ceremony to happen at Rahul's room | Maharaja Suite
| Janki to get ready (HMU) for photoshoot |  | 15:00 | 17:30
| Couples photoshoot | Photo & Video team | 17:30 | 18:30
| Snacks & Dinner with few guests of the couple | Promenade - UDV | 18:30 | 21:30 |  | Small Bar
| Family Rehearsals for sangeet with Soochna Choreographer | Ballroom | 22:00 |  |  | Boom box required
28th October- DAY 2
| Breakfast for overnight guests |  | 7:30 | 10:30
Guest Check-ins
| Couple & Family Interviews |  | 10:00 | 12:30
| Lunch | Dining Room | 12:00 | 14:00 |  | *Easy Music
Speakers + Pool Floats on standby
Beers & Soft beverages to be served by hotel in disposable glasses
| Pool gathering |  | 12:00 | 16:00 | *pen drive for speakers | *only beer & soft beverages to be served by hotel (in disposable glasses only). *floats & speakers
| Janki's Mehendi by the pool |  | 13:00 | 15:00
| Mehendi for 5 Family Members to begin | Room/Pool
| Cake for bday celebration on standby | Room
| Cake cutting for Krishaang & Ishaan's birthday | Room | 15:00
| Guest Salon Opens | Kangan | 15:00 | 19:00
| Janki Hair & Makeup |  | 17:30 | 20:00
| Sound Check for Gurdeep | Mewar Room | 17:30
| Sangeet Guest Arrival begins | Inner Courtyard | 19:00 |  |  | * cue cards for emcee (Rahul's friend). *seats blocked for families
| Rajasthani Dancers |  | 19:00 | 19:30 |  | ( inhouse hotel, need to inform the hotel on time)
| Drinks & Canapaes |  | 19:00 |  |  | As soon as the guest arrive
Pranav & Parul to open the night
| Snacks serving to begin |  | 20:30 |  |  | Snacks service to continue at the back once the family performance starts
| Couple Games |  | 20:15 | 20:30 |  | Check with Parul for props
| Family Performance |  | 20:30 | 21:15 |  | Radhika will advise on the no. of performance
| Speeches |  | 20:00 | 20:15 |  | * cue cards for speeches
| Dinner Opens | Mewar Terrace | 21:30 | 12:30 |  | * food props styling each counter
| Video/PPT Slideshow to be played on LED Screen From Parul |  | 21:30 | 22:30
| Gurdeep Mehendi | Mewar Hall | 22:30 |  |  | * refreshments & cold towels for Gurdeep's team at sound check. *Green Room for Gurdeep's band
| Dj Amit to take over | Mewar Hall | 12:30
| After Party | Mewar Hall | 1:30
| After party menu to be served |  | 1:30 | 3:30
29th October
| Breakfast |  | 8:00 | 11:00
| Cricket Match | Lawns | 12:30 | 14:00 |  | * Shading, Bar station, Cold Towel, Mic, Led Screen, 2 Camera Setup, 7 Trophy , Umbrella
*Beer, Dj, Rules Flags, Score Card, Tshirt, Commentor, Sounds, Caps, Whistles
| Lunch | Dining Room | 13:00 | 15:00
| Guest Salon |  | 14:00 | 17:00 |  | * saree draper & hair stylist to be ready in salon
| Sound Check for Salman Ali |  | 14:00 |  |  | * cold towels & refreshments for Salman Ali's team
| Janki Hair & Makeup |  | 15:00 | 18:00
| DJ Amit to begin ambience musix |  | 15:00
| Guest Arrival For Mehendi | Guava Gardens | 17:00 |  |  | * caricature artist, lakh bangle & rajasthani dancers
| Rajasthani Dancers on standby for guest welcome |  | 17:00 |  |  | ( inhouse hotel, need to inform the hotel on time)
| Guest Mehendi |  | 17:00 | 20:00 |  | * dance orders from choreographer
| Snacks & bar service to begin |  | 17:00
| Salman Ali |  | 19:30 | 21:00 |  | * green room & fan for Salman Ali
| Chat Station to open |  | 18:00 | 20:00
| Dinner opens |  | 20:00
| DJ Amit to take over the Mehendi |  | 21:00 | 22:30
| Karaoke setup to be ready for Pyjama after party | Ballroom | 20:00 |  |  | No Food & Bar at the Ballroom
| Boombox setup at Rahul & Janki's room to be ready | Royal & Maharaja Suite | 21:00
30th October | Breakfast |  | 7:30 | 10:30
| Harsh Pandit to setup arrangements for Janki's Mandva | Inner Courtyard | 8:00
| Chair Arrangement for 60 PAX to be done for Mandva | Inner Courtyard
| Janki's Mandva (Approx 60 PAX) | Inner Courtyard | 9:00 | 10:00 |  | 60 chairs from Aneesa
Dholwala on standby for bhaat
| Rahul Bhaat in his room for 20 PAX | Maharaja Suite | 10:00
Curd, Grass, Baby Oil, Haldi to be arranged for haldi ceremony
| Haldi | Inner Courtyard | 10:30 | 12:30 |  | *tissue paper and water
| Guest Salon |  | 10:00 | 15:00
| Lunch |  | 12:00 | 14:00
| Janki Hair & Makeup |  | 12:00 | 15:30
| Photoshoot |  | 15:30 | 16:00
| Safa Bandi for groom side | poolside | 15:30 | 16:00 |  | * Safa Wala
| Safa Bandi for bride side | Library Bar | 16:30
| Baraat |  | 16:30 | 17:30 |  | * Vintage car, Dhol Players, cold towels, gola stalls, stationary speakers, fan
| Baraat Hi-Tea |  | 16:30 | 18:30
| Milni |  | 17:00 | 17:30 |  | * garlands
| Vandana to begin singing |  | 17:00
| Wrap hi tea setup |  | 18:30
| Groom Entry |  | 17:00 | 17:30 |  | Entry songs by vandana
| Bridal Entry with flower girls & Flower chaddar |  | 17:30
Varmala Exchange
Bride to exit & wait at sheesh mahal and pooja ceremony for rahul at mandap
| Bride entry for mandap |  |  |  |  | Entry song by vandana
| Pheras | Outer Courtyard | 17:45 | 18:45 PM |  | * cold towels, Vandana to sing with 2-3 pax (flute, shehnai, harmonium). * 1 sweet box 1/2 kg
| Family photos (Groupwise) |  | 19:00 | 19:15
| Bridal Exit Ceremony with Rice & flower petals - Check with Mrs Sangwan | Outer Courtyard
| Pooja ceremony in Rahul's room |  | 19:15 | 19:30
| Couple to change |  | 19:30 | 20:00
| Starters & Bar to begin |  | 19:00
| Guests to be seated at designated seats |  | 20:15
Announcement to be made for the couple and wedding entourage entering
| Couple Entry |  | 20:30
First Dance
| Dinner Opens |  | 20:30
| Speeches ( 6 PAX) |  | 20:45
| Post Wedding Rituals |  |  |  |  | * 1 big paraath & Kum-Kum for post wedding games- Mrs. Sanghwani
| After party with DJ Amit | Marwar Hall

## Checklist
Private & Confidential
27th October - Welcome Dinner
Sr No | Description | Responsibility | Deadline | Status | Remarks
Cars from Airport to Nathdwara
2-3 Wheel chairs with attendant for Nathdwara VIP darshan to be arranged
4-5 innova to be arranged
3 Rooms for Mrs Sangwan's HMU (6 Pax)
Ganesh Stapana at Inner Courtyard on Oct 30
Engagement on Oct 27 for 30-40 pax
| Pooja in Rahul's room on Oct 30 (Who is the panditji) | Nat / Show Runners
| 1 Big thal for Mrs Sangwan for bridal gifts | Nats/Chirag/Sakshi/Show Runner
| 2 Chowkis from Oct 27 to Oct 30 in Rahul's room - Mrs Sangwan | Chirag /Nat
| 1 Local Pandit for the engagement locally for engagement @ Royal Suite- Rahul | Chirag /Nat
| 2 kgs sweets for engagement | Mona
| Pooja Thal with Diya & Ganesh idol for engagement - Mrs Sangwan | Chirag /Nat
| Floats for pool party + Boom Box | Leela/Chirag |  |  | Hotel has few, few to be sourced by Chirag, Chirag has boom box
| Plastic glasses for Pool Party | Chirag
| Photoshoot followed by Interviews - 5:30 to 6:30 PM | HOTC/Nats
28th October
Sr No |  | Responsibility | Deadline | Status | Remarks
| Guest hotel welcome | Leela
| Finalise the salon area at the hotels (Kangan/Bindiya) | Mona
| Salon Vendors to be finalized and blocked | Iris
| Family requirements for florals in hair - Sangwan Family | Iris
| Family requirements for florals in hair - Bhimjiyani Family | Iris
| Refreshments & cold towel to be there for Gurdeep mehendi's team for sound check | Show Runners
| Sequence of acts from Choreographer | Show Runners/Soochna Choreographer
| Need the family performance tracks ona pendrive | Show Runners/Soochna Choreographer
| Cue cards for emcee & family speeches (Rahul's friend as emcee at Sangeet) | Mona/ Show Runners
| Blocking of seats for family | Mona
| Table Stands with Table numbers | Sakshi
29th October
Sr No |  | Responsibility | Deadline | Status | Remarks
| Tshirt , Pom-Pom, Whistle to be ready for cricket match | Chirag /Nat/Show Runners
| Saree drapper, hair stylist to be ready for guest salon | Hospitality
| Refreshments & cold towels for salman ali team during sound check | Mona/Showrunners
| Mehendi - Stalls lac bangle maker caricature artist | Chirag/Nat/Anisa |  |  | Ask Chirag on Caricature Artist requirmentsInform Anisa about platform size for Lak bangle
| Fan for salman ali team during Sound check & Show | Dhruv/Hiren
| Dhol wala for Bhaat function - Mrs Sangwan | Chirag/Nat/Show Runners
| Coolers for Mehendi Function | Dhruv/Hiren
30th October
Sr No |  | Responsibility | Deadline | Status | Remarks
| Tissue paper and water to be arranged for haldi functions | Nat/Show Runers/Sakshi/Shahi Taj Pagadi
| Safa wala to be ready for groom & Bride side | Nat/Show Runers/Sakshi
| Colorful Umbrella for Rahul during Baarat | Nat/Show Runers/Sakshi
| Cold towels for Baraat | Mona/Leela
| Cold towels for Wedding Ceremony | Mona/Leela
| Baraat Vintage Car + 1 Colorful Umbrella + 2 Dhol Wala | Nats/Chirag/Show Runner/Sakshi
| Stationary speakers + Fan/Cooler on the baraat route | Dhruv/ Hiren
| Bridal + Groom + Varmala entry song from Janki | Vandana Masi/Nats/Show Runner
| Phera Ritual Samagri from Rupa B & Panditji | Nats/Show Runner
| Figure out emcee from family for reception | Mona
| Pre-recorded introductions of family for reception dinner entries from Janki & Rahul | Mona
| Tracks from Mrs. Sangwan | Mona
| Couple Entry (Parent - Sister - Couple) | Nats/Show runner
| First dance track Medely track to be taken from Janki | Mona
| Cue Cards for speeches | Nats/Show runner
| 1 Sweet box half kg for wedding ceremony | Mona/JMB
| Mogra garlands for Milni - Mrs Sangawan | Anisa
| Jaimala | Anisa
| Loose flower petals for phera | Anisa/Sakshi/Show Runner
| 1 big paarath with a packet of Kum Kum for games post wedding - Mrs Sangwan | Nats/Chirag/Sakshi/Show Runner
Other Pointers
Sr No |  | Responsibility | Deadline | Status | Remarks
| Thank you Gift | Hospi
| welcome hampers for all guests | Hospi
| collaterals & signages | Mona
| get boombox for - dance rehearsal on 27th & 28th | Chirag
| Tailor - check with janki do we need or not | Mona/Chirag/Natasha
Shehnai wala on wedding day - Mrs Sangwan - Vandana (wedding singer)
Dholwala for Oct 29 - Mrs Sangwan
| JR Logo to be designed by Itcha | Iris
SFX for Wedding (Cold Pyros, Shower Petal)
JR Logo for Gobo
| Enetrtainment by Leela at porch (Harmonium etc) to be there for all days | Mona/Leela

## MOM 7th June
Wedding Celebrations of Janki & Rahul
Minutes of Meeting - Call on 7th June
Event Dates | 27/28/ 29 / 30 October
Attendees | Janki, Rauhl & Zoé
GENERAL POINTS | Jagmandir details to be sent & venue to be blocked. Payment to be made asap
Meera - to give price for another +3 family members
Meera - Janki half look between ceremony & reception
Shadows hair salon - to be blocked for guests
Speak to Amit - re: Pool gathering
20 seats blocked on Janki's & Rahul's fllight - enquiry to be made for pricing
ANCILLARY ACTS / ITEMS | PPT to be made of all suggested ancillary - to start on this next week
- eg mehendi walis
- dhol walas
- vintage vehicle
- stalls (lak bangle, paan stall, gola stall etc)
- cricket match requirements (T Shirts etc)
- fire throwers at Mehendi sundowner
- Wedding cake options
- Couple entries
ITCHHA - ITINERARY | Different versions for Janki & Rahul
Janki:
Nathdwara
Jagmandir
Ganesh Puja
Pool gathering
Sangeet
Cricket match
Mehendi sundowner
Pajama party
Haldi
Wedding
Reception
Rahul:
Jagmandir
Puja
Pool gathering
Sangeet
Cricket match
Mehendi sundowner
Haldi
Baraat
Wedding
Reception
DECOR:
Sangeet: | - Flex options discussed, 1) Invert the white/black option to bottle green with gold 2) Black/ White geometirc with foliage option
- Forest tunnel (greens/whites/hints of gold) to have hints starting from walkway from lobby to halls
- Tunnel to be in corridor between two rooms
- Photo op to be re thought of
- Fairy lights over terrace to be considered
- Dancefloor to be 24x12
- Deep greens/ bronzes/ gold preferred
- Flex frame around LED to be considered? Or artificial foliage - both options to be shared
- Bar facia to be used as per moodboard (green & gold)
- Velvet tablecloths liked to be used as per moodboard (dusty pinks/ turqoise - ish)
- Green & gold baubles and leaves etc to be used as low centre pieces (as per moodboard) - "Christmas" look to be made not so Chrismassy
Mehendi:
- Colour palette Mediterranean lemon yellow, blues, whites, macrame - no pinks
- Entry & walkway to Mehendi to be clarified
- Trees to be wrapped in fairy lights - some lamps to be hanging from trees
- Bridal swing to be as per previous MEW Leela event
- No arches over food
- Replacement options for arches over stage & bar - to be more full and not strings/ sparse
- No barn like looks ie the bar is untreated ply wood - need more options
- Consider options for chair covers/ ties
- Replace high chairs with other options
- Gaddas to have back rests
Wedding: | - Colour palette is fine
- Mirror table covers
- Chandelier type tea light stands
- Mood board to follow the look of Sonali Fabiani wedding
- High elegant centre pieces
WAY FORWARD | Payment schedule to be made - for all deposits to be made within month of June
Photographer options sent - to be closed asap
Jagmandir info to be sent
Payments to be made to:
Shadows guest salon
DJ Amit
Jagmandir
Photographer

## Mom - 14th June
Wedding Celebrations of Janki & Rahul
Minutes of Meeting - Call on 14th June
Event Dates | 27/28/29/30 October
Attendees | Janki, Janki's mom and Rahul's mom & Iris
HAMPERS/THANK YOU GIFTS | Hamper Options ppt shared with Rahul & Janki
Thank you gift options to be shared
Guest would like to keep Mehendi Gifts - options to be shared
ANCILLARY ACTS / | Perfume Bar - Mehendi - Price to be shared
Laq Bangles - Mehendi - Price to be shared
Discuss with Rahul and Janki with they would like to keep gaames for mehendi
Mehendiwali for the brIde to be blocked - Bridal Mehendi Timing to be finalised
Hair Stylist and Saree Draper - blocked - guest to be charged price to be finalised
EVENT FLOW | Small other Pooja ritual Timings and venues to be finalised
Sagaai & Tikka ( Tentative : 28th morning @10:00 am)
Godh Baharai ( 28th morning)
Ganesh Stahapna - will require havan (29th morning)
Haldi - 29th morning
Bhaat Ceremony
Bidaai and post wedding games
Rahul's mom would like us to make an announcement and introduce the family before the couple enters
Tentative Wedding Day Intinerary
4:00 pm Baraat
5:00 - 6:30 pm Wedding
6:30 pm onwards ( Family & Couple pictures)
Bara and Snacks service to start for guests
07:30 pm : Announcement for guest to be seated
07:45 pm: Families to introduced and called on the center stage
07:55 pm : Couple to enter ( Cake cutting, speeches, first dance .....)
8:30 PM : Dinner to be served
Entire event flow to be rediscussed

## MoM - June 20-21
Wedding Celebrations of Janki & Rahul
Minutes of Meeting - Call on 20-21 June, 2022
Event Dates | Oct 27 to 30, 2022
Attendees | Rahul, Janki, Iris, Adi, Zoé & Saival
DISCUSSION POINTERS
Day 0 - Nadthwara transfers (3 elderly) - VIP Darshan to be arranged, 3 wheelchairs + attendants to be arranged. 4-5 Innovas to be organised.
Day 0 Dinner Options: Jagmandir, City Palace terrace restaurant, UDV Suryamahal restaurant
Day 0 Dinner - MEW to get menus, alcohol costs
Day 0 Dinner - Local singer to be shared
Family butlers/ shadows
Hamper options - details shared
Pocket squares / dupatta / potlis - prices shared
Saree draper
Perfume bar cost, mela cost - bindis, mangtikkas
Box cricket format to be played at Croquet Lawns, nets placed around with artificial turf pitch, 8 players per side, tennis ball?, commentator, umpire & score board, Bride vs Groom side Tshirts, pom poms & whistles
Mehendi ancillary costs - fire blowers, folk dancers, nagada drummers, tarot reader, palm reader, caricaturist
Baraat vehicle - vintage red car
Baraat - gola stall, dhol walas, stationary speakers, fans/ coolers
HOTC confirmed - interviews & couple photoshoot to be scheduled
Rahul's friend as emcee at Sangeet
Wedding maharaj to arrive on 29th last flight Oct 30th Mandvo pooja, check with maharaj on samagri list
Prerecorded introductions of family for reception dinner entries
JB's mother's cousin to sing during wedding - 2-3 pax with shenai, flute & harmonium, MEW to check on tech requirements
Feedback on reception band
Leela has confirmed the same contracted rate will be applicable for rooms required on 26th ( Suite prices will be different) room count to be shared
Itinerary | Day 0
Bride arrives
Groom arrives
Nadthwara visit
Couple pre wedding shoot
Jagmandir dinner
Day 1
Guest arrivals & check ins
Rehearsals
12:00 - 14:00 - Pool Gathering
14:00 - 18:00 - Bridal Mehendi & Family Mehndi ( Sonamistry blocked)
Lunch TBC
16:30 - 19:30 - Bride HMU
19:40 - 20:10 - Couple photos
20:15- Couple entry
20:30 - Speeches
21:00 - 21:45 - Family performance
22:00 Dinner opens
22:30 - Gurdeep Mehdni performance
Day 2
09:00 - 11:00 - Breakfast
12:00-14:00 - Cricket
13:30 - 14:30 - Lunch
15-17:30 - Bride HMU
17:00 - 22:00 - Guest arrivals
17:00: Mehendi for guests. ( Local artist to be blocked)
17:30 - 19:30 - DJ Amit
17:30 - 18:00 - Bride photos
18:00 - Bridal entry
18:30 - Groom entry
19:00 Ancillary act
19:30 - 21:00 - Salman Ali performance
21:00- 22:00 - DJ Amit
22:00 onwards PJ party
Day 3
09:30 - 10:30 - Bride Mandvo / Groom Baath
10:30 - 11:30 - Haldi
12:30 - 15:30 - Bride HMU
14:30 - 15:00 - Groom photos
15:00 - 16:00 - Sehra Bandhi
15:30 - 16:00 - Bride photos
16:00-17:00 Baraat
17:15 - 18:15 Pheras
18:15 - 18:45 Family photos
18:15 Bar & pass arounds begin
18:45 - 19:30 Couple change
19:35 - Couple entry
20:00 - Sit down service begins / Buffet opens
20:30 - Speeches
20:45 - 10:15 Band performs

## MoM- 7th Oct
Wedding Celebrations of Janki & Rahul
Minutes of Meeting - Call on 7th Oct,2022
Event Dates | Oct 27 to 30, 2022
Attendees | Rahul, Janki, Iris, Saival, Mona,Heena,Dhruv & Natasha
DISCUSSION POINTERS
Pre recorded tracks for Pool party to be carried by DJ
Games for Pool - Janki wants some team based interactive games
Janki to get back who from family can conduct the pool party
Iris to share anchor options locally for pool party games
Reserve Tags for sangeet by MEW, family to identify members for reserved seating
Whistles for sangeet to be sourced
Couple entry for sangeet - JR Will get back if they want an entry or not
MEW to speak to Radhika for the Sangeet Performance flow
Pranay & Ronak - Sangeet Emcee - Can mew plan a rough flow of how can they conduct
2 boombox for Janki and Rahul for each room post after party
Speak to pandit ji - Janki enters once and twice between jaimaal & wedding
Garlands from Anisa for Milni - Janki is already discussing the details, she will let us know
Phera Ritual Samagri - Everythig is being carried by Panditji
Baskets & flower petals for flower girls for jaimaal entry - Janki to conifrm names & number of girls
JR Entry song for reception - They will get back
First dance track from Janki - Follow up later, track is WIP
Janki to confirm who will be the emcee for reception entries
Reception entry flow - Siblings - Parents - Couple
Tailor - Not required as discussed with Janki
Tshirt printing under process
JR to finalise the seating plan for the reception dinner
Rooming list to be shared with the hotel by 08th October
Food and Beverage | Awaiting Leela confirmation for Main Menu, Breakfast Menu and Lounge Menu.
Saival to get back on the service of alcohol for Udaivilas dinner (either will be charged on comsumption or bottle price)
Rahul to identify the guests who will be invited for the Promenade dinner.
Janki to share PJ party menu with Mona
Masala Chai after events : will be charged at INR 250 ++ per person
Cake for 28th for two guests. Janki to share details with Mona.
Beer and soft beverage to be served at the Pool Party & Cricket Match
Hampers | Contents list shared. Awaiting packaging details.
Gifting :(1) welcome hamper (2) Janki's PJ gifts (3) Potli/ Dupatta (4)Mrs Sangwan's sweets + clothes
Collaterals | Awaiting design of ritual booklet.

## MoM- 11th Oct
Wedding Celebrations of Janki & Rahul
Minutes of Meeting - Call on 11th Oct,2022
Event Dates | Oct 27 to 30, 2022
Attendees | Rahul, Janki, Iris, Saival, Mona,Heena,Dhruv & Natasha
DISCUSSION POINTERS
Check on VIP booking for 13 people of darshan for Janki's family to Nathdwara
Janki to get back who from family can conduct the pool party
Check the guest arrival sheet on 27th to figure dinner and drinks arrangements for them
Check what time will we get Suites of couple for 27th
Check if we can do a speaker setup at pool party - TBD between Saival & Rahul
Some games for pool party that can be conducted without an emcee
Suggestions on songs for entry by MEW
Share pictures of sword and royal chattar with client
Share communication of Mandva & Bhaat separately with respective guestlist
Client is getting thali and chowki for all pooja ceremony, MEW to not arrange for them
Sangeet - They would like an entry, suggest songs
Reception entry - First dance to happen before or after speeches - TBD

## MoM- 15th Oct
Wedding Celebrations of Janki & Rahul
Minutes of Meeting - Call on 11th Oct,2022
Event Dates | Oct 27 to 30, 2022
Attendees | Rahul, Janki, Iris, Saival, Mona,Heena,Dhruv & Natasha
DISCUSSION POINTERS | Check with chirag on marshal speakers for promenade
Make playlist for dinner on 27th
After party venue to be closed
Check with janki who can she entre with her for her mehendi
Rehearsal dinner
Event flow run with couple to be done

## Crew TLB
Sr. No. | Team | Role | Salutation | First Name | Last Name | Room Count | HOTEL | Room Category | Check in date | Check out date | 26th Nov | 27th Nov | 28th Nov | 29th Nov | 30th Nov | 31st nov | Sector | Class | Arrival Date | Flight Number | Arrival Time | Sector | Departure Date | Flight Number | Departure Time | Luggage Allowance | Rooming Nights | Per Night Cost | Total Hotel Cost | Aprox Flight Cost | Remark | Per Diems Allowance | No. Of Days | Total Per Diems | Remarks for Perdiems
1 | MEW | Director | Mr | Aditya | Motwane | 1 | Leela | Double Occupancy | 2022-10-28 | 2022-10-31 |  |  | 1 | 1 | 1 |  | BOM-UDR | Biz | 2022-10-28 | UK 613 | 13:45 | UDR-BOM | 2022-10-31 | UK 614 | 14:20 |  | 3 | Leela | 0 | 47800 |  | 0 | 0 | 0 | Venue
2 | MEW | Client Service | Ms | Zoé | Blues | 0 | Leela | Double Occupancy | 2022-10-28 | 2022-10-31 | [6 empty] | BOM-UDR | Eco | 2022-10-27 | UK 613 | 13:45 | UDR-BOM | 2022-10-31 | UK 614 | 14:20 |  | 3 | Leela | 0 | 21241 | Cancel and Re issue | 2500 | 1 | 2500 | Per Diem
3 | MEW | Client Service | Ms | Zoe | Blues | 1 | RL | Single Occupancy | 2022-10-27 | 2022-10-28 |  | 1 |  |  |  |  | - | - | - | - | - | - | - | - | - |  | 0 |  |  | 0 |  | 0 | 0 |  | Per Diem
4 | Shadow | Mrs Bhimjiyani | Ms | Rachana | More | 1 | RL | Double Occupancy | 2022-10-27 | 2022-10-31 |  | 1 | 1 | 1 | 1 |  | BOM-UDR | Eco | 2022-10-27 | UK 613 | 13:45 | UDR-BOM | 2022-10-31 | UK 614 | 14:20 |  | 4 | 7500 | 30000 | 21878 |  | 2500 | 4 | 10000 | Per Diem
5 | MEW | Entertainment | Ms | Natasha | Mour | 0 | RL | Double Occupancy | 2022-10-27 | 2022-10-31 | [6 empty] | BOM-UDR | Eco | 2022-10-20 | UK 613 | 13:45 | UDR-BOM | 2022-10-31 | UK 614 | 14:20 | 15kg | 0 | - | - | 28628 | 6750 Luggage cost | 2500 | 4 | 10000 | Per Diem
6 | MEW | Tech/Pro | Mr | Saival | Jaradi | 1 | RL | Double Occupancy | 2022-10-26 | 2022-10-31 | 1 | 1 | 1 | 1 | 1 |  | BOM-UDR | Eco | 2022-10-26 | UK 613 | 13:45 | UDR-BOM | 2022-10-31 | UK 614 | 14:20 |  | 5 | 7500 | 37500 | 15470 |  | 2500 | 5 | 12500 | Per Diem
7 | MEW | Crew TLB | Mr | Ishen | Patel | 0 | RL | Double Occupancy | 2022-10-26 | 2022-10-31 | [6 empty] | BOM-UDR | Eco | 2022-10-26 | UK 613 | 13:45 | UDR-BOM | 2022-10-31 | UK 614 | 14:20 |  | 0 | - | - | 15470 |  | 2500 | 5 | 12500 | Per Diem
8 | MEW | Hosp Head | Ms | Iris | Tung | 1 | RL | Double Occupancy | 2022-10-26 | 2022-10-31 | 1 | 1 | 1 | 1 | 1 |  | BOM-UDR | Eco | 2022-10-26 | UK 613 | 13:45 | UDR-BOM | 2022-10-31 | AI 644 | 16:30 |  | 5 | 7500 | 37500 | 16140 |  | 2500 | 6 | 15000 | Per Diem
9 | MEW | Hosp Co Head | Ms | Ramandeep | Sablok | 0 | RL | Double Occupancy | 2022-10-26 | 2022-10-31 | [6 empty] | BOM-UDR | Eco | 2022-10-26 | UK 613 | 13:45 | UDR-BOM | 2022-10-31 | NA | NA |  | 0 | - |  | 7870 |  | 2500 | 5 | 12500 | Per Diem
10 | MEW | Hamper and Other | Ms | Dipal | Suru | 1 | RL | Double Occupancy | 2022-10-26 | 2022-10-31 | 1 | 1 | 1 | 1 | 1 |  | BOM-UDR | Eco | 2022-10-26 | UK 613 | 13:45 | UDR-BOM | 2022-10-31 | NA | NA |  | 5 | 7500 | 37500 | 12116 | One way cancel | 2500 | 5 | 12500 | Per Diem
11 | MEW | Crew TLB | Ms | Sakshi | Agarwal | 0 | RL | Double Occupancy | 2022-10-26 | 2022-10-31 | [6 empty] | BOM-UDR | Eco | 2022-10-26 | UK 613 | 13:45 | UDR-BOM | 2022-10-31 | UK 614 | 14:20 |  | 0 | - |  | 15470 |  | 2500 | 5 | 12500 | Per Diem
12 | MEW | F&B | Ms | Monalisa | Philips | 1 | RL | Double Occupancy | 2022-10-26 | 2022-10-31 | 1 | 1 | 1 | 1 | 1 |  | BOM-UDR | Eco | 2022-10-26 | UK 613 | 13:45 | UDR-BOM | 2022-10-31 | UK 614 | 14:20 |  | 5 | 7500 | 37500 | 15470 |  | 2500 | 5 | 12500 | Per Diem
13 | MEW | Hosp Co Head | Ms | Heena | Kadhi | 0 | RL | Double Occupancy | 2022-10-26 | 2022-10-31 | [6 empty] | BOM-UDR | Eco | 2022-10-26 | UK 613 | 13:45 | UDR-BOM | 2022-10-31 | AI 644 | 16:30 |  | 0 | - |  | 16140 |  | 2500 | 6 | 15000 | Per Diem
14 | MEW | TLB (Overall) | Mr | Vivek | Agre | 1 | RL | Double Occupancy | 2022-10-26 | 2022-10-31 | 1 | 1 | 1 | 1 | 1 |  | BOM-UDR | Eco | 2022-10-26 | UK 613 | 13:45 | UDR-BOM | 2022-10-31 | UK 614 | 14:20 |  | 5 | 7500 | 37500 | 16000 |  | 2500 | 5 | 12500 | Per Diem
15 | MEW | Guest/Artist Logistics | Mr | Lokesh | Agre | 0 | RL | Double Occupancy | 2022-10-26 | 2022-10-31 | [6 empty] | BOM-UDR | Eco | 2022-10-26 | UK 613 | 13:45 | UDR-BOM | 2022-10-31 | AI 644 | 16:30 |  | 0 | - |  | 16670 |  | 2500 | 6 | 15000 | Per Diem
16 | MEW | Guest/Artist Logistics | Mr | Saif | Qureshi | 1 | S | Double Occupancy | 2022-10-26 | 2022-10-31 | 1 | 1 | 1 | 1 | 1 |  | BOM-UDR | Eco | 2022-10-26 | UK 613 | 13:45 | UDR-BOM | 2022-10-31 | AI 644 | 16:30 |  | 5 | 7500 | 37500 | 16670 |  | 2500 | 6 | 15000 | Per Diem
17 | MEW | Prod Usher | Mr | Durgesh | Mandal | 0 | RL | Double Occupancy | 2022-10-26 | 2022-10-31 | [6 empty] | BOM-UDR | Eco | 2022-10-26 | UK 613 | 13:45 | UDR-BOM | 2022-10-31 | AI 644 | 16:30 |  | 0 | 7500 |  | 16670 |  | 2500 | 6 | 15000 | Per Diem
18 | MEW | Prod Cord Head | Mr | Hiren | Sonawala | 1 | RL | Double Occupancy | 2022-10-26 | 2022-10-31 | 1 | 1 | 1 | 1 | 1 |  | BOM-UDR | Eco | 2022-10-26 | UK 613 | 13:45 | UDR-BOM | 2022-10-31 | AI 644 | 16:30 |  | 5 | 7500 | 37500 | 16670 |  | 2500 | 6 | 15000 | Per Diem
19 | MEW | Prod Cord Head | Mr | Dhruv | Desai | 0 | RL | Double Occupancy | 2022-10-26 | 2022-10-31 | [6 empty] | BOM-UDR | Eco | 2022-10-26 | UK 613 | 13:45 | UDR-BOM | 2022-10-31 | AI 644 | 16:30 |  | 0 |  |  | 25552 |  | 2500 | 6 | 15000 | Per Diem
20 | MEW | Show Run | Mr | Aman | Rawat | 1 | RL | Double Occupancy | 2022-10-28 | 2022-10-31 |  |  | 1 | 1 | 1 |  | BOM-UDR | Eco | 2022-10-28 | UK 613 | 13:45 | UDR-BOM | 2022-10-31 | UK 614 | 14:20 |  | 3 | 7500 | 22500 | 16370 |  | 2500 | 3 | 7500 | Per Diem
21 | MEW | Show Run | Mr | Suhit | Otswal | 0 | RL | Double Occupancy | 2022-10-28 | 2022-10-31 | [6 empty] | BOM-UDR | Eco | 2022-10-28 | UK 613 | 13:45 | UDR-BOM | 2022-10-31 | UK 614 | 14:20 |  | 0 | - | - | 16370 |  | 2500 | 3 | 7500 | Per Diem
22 | Events XO | Decor | Ms | Heena Anisa | Kapoor | 1 | Leela | Single Occupancy | 2022-10-27 | 2022-10-31 |  | 1 | 1 | 1 | 1 |  | - | - | 2022-10-27 | - | - | - | 2022-10-31 | - | - |  | 4 | Leela | 0 | 0 |  | 0 | 0 | 0 | Venue
23 | Events XO | Decor | Ms | Heena Anisa | Kapoor | 1 | RL | Single Occupancy | 2022-10-26 | 2022-10-27 | 1 | [5 empty] | DEL-UDR | Eco | 2022-10-26 | UK 627 | 14:45 | UDR-DEL | 2022-10-27 | UK 628 | 15:20 |  | 1 | 7500 | 7500 | 13680 |  | 2500 | 1 | 2500 | Per Diem
24 | Events XO | Decor | Mr | Rajat | Maheshwari | 1 | RL | Single Occupancy | 2022-10-26 | 2022-10-31 | 1 | 1 | 1 | 1 | 1 |  | DEL-UDR | Eco | 2022-10-26 | UK 627 | 14:45 | UDR-DEL | 2022-10-31 | UK 628 | 15:20 |  | 5 | 7500 | 37500 | 13680 |  | 2500 | 6 | 15000 | Per Diem
25 | Bar team | Bartending | Mr | Nikhil | Bhagat | 1 | Hibiscus | Double Occupancy | 2022-10-28 | 2022-10-31 |  |  | 1 | 1 | 1 |  | BOM - UDR | Eco | 2022-10-28 | UK 613 | 13:45 | UDR-BOM | 2022-10-31 | UK 614 | 14:20 | 10 kgs | 3 | 4400 | 13200 | 52373 |  | 2500 | 3 | 7500 | Per Diem
26 | Bar team | Bartending | Mr | Yogesh | Shinde | 0 | Hibiscus | Double Occupancy | 2022-10-28 | 2022-10-31 | [6 empty] | BOM - UDR | Eco | 2022-10-28 | UK 613 | 13:45 | UDR-BOM | 2022-10-31 | UK 614 | 14:20 | 10 kgs | 0 | - |  | 16373 |  | 2500 | 3 | 7500 | Per Diem
27 | Bar team | Bartending | Mr | Adithya | Vaman | 1 | Hibiscus | Double Occupancy | 2022-10-28 | 2022-10-31 |  |  | 1 | 1 | 1 |  | BOM - UDR | Eco | 2022-10-28 | UK 613 | 13:45 | UDR-BOM | 2022-10-31 | UK 614 | 14:20 | 10 kgs | 3 | 4400 | 13200 | 16373 | 36000 baggage | 2500 | 3 | 7500 | Per Diem
28 | Bar team | Bartending | Mr | Ashutosh | Patil | 0 | Hibiscus | Double Occupancy | 2022-10-28 | 2022-10-31 | [6 empty] | BOM - UDR | Eco | 2022-10-28 | UK 613 | 13:45 | UDR-BOM | 2022-10-31 | UK 614 | 14:20 | 10 kgs | 0 | - |  | 16373 |  | 2500 | 3 | 7500 | Per Diem
29 | HOTC | Photo & Video | Mr | Ashwin | Kumar | 1 | Trident | Single | 2022-10-27 | 2022-11-01 |  | 1 | 1 | 1 | 1 | 1 | BLR-UDR | Eco | 2022-10-27 | 6E6091 | 13:20 | UDR-BLR | 2022-11-01 | 6E412 | 11:00 | 10 kgs | 5 | 16500 | 82500 | 39600 | 13500 * 3 baggage | 0 | 0 | 0 | Venue
30 | HOTC | Photo & Video | Mr | Vivek | Kashyap | 1 | Trident | Double Occupancy | 2022-10-27 | 2022-11-01 |  | 1 | 1 | 1 | 1 | 1 | BLR-UDR | Eco | 2022-10-27 | 6E6091 | 13:20 | UDR-BLR | 2022-11-01 | 6E412 | 11:00 | 10 kgs | 5 | 16500 | 82500 | 26100 |  | 0 | 0 | 0 | Venue
31 | HOTC | Photo & Video | Mr | Lonav | Bharali | 0 | Trident | Double Occupancy | 2022-10-27 | 2022-11-01 | [6 empty] | GAU-DEL-UDR | Eco | 2022-10-27 | 6E 6394 6E 6264 | 18:50 | UDR-DEL-GAU | 2022-11-01 | 6E 6789 6E 889 | 12:45 | 10 kgs | 0 | - | - | 35060 |  | 0 | 0 | 0 | Venue
33 | HOTC | Photo & Video | Mr | Chitresh | Mishra | 1 | Trident | Double Occupancy | 2022-10-27 | 2022-11-01 | [6 empty] | DEL-UDR | Eco | 2022-10-27 | UK 627 | 14:45 | UDR-DEL | 2022-11-01 | AI 472 | 15:05 | 10 kgs | 0 | - | - | 10950 |  | 0 | 0 | 0 | Venue
34 | HOTC | Photo & Video | Mr | Yogananda | J S Ramesh | 0 | Trident | Double Occupancy | 2022-10-27 | 2022-10-31 |  | 1 | 1 | 1 | 1 |  | DEL-UDR | Eco | 2022-10-27 | UK 627 | 14:45 | UDR-DEL | 2022-10-31 | AI 472 | 15:05 | 10 kgs | 4 | 16500 | 66000 | 6300 | Cancelation cost only | 0 | 0 | 0 | Venue
32 | HOTC | Photo & Video | Mr | Shiva | Kumar M | 1 | Trident | Double Occupancy | 2022-10-27 | 2022-10-31 |  | 1 | 1 | 1 | 1 | 1 | BLR-UDR | Eco | 2022-10-27 | 6E6091 | 13:20 | UDR-BLR | 2022-10-31 |  |  | 10 kgs | 4 | 16500 | 66000 | 32317 |  | 0 | 0 | 0 | Venue
35 | HOTC | Photo & Video | Mr | Thilak Chandra |  | 0 | Trident | Double Occupancy | 2022-10-27 | 2022-10-31 | [6 empty] | BLR-UDR | Eco | 2022-10-27 | 6E6091 | 13:20 | NO RETURN | 2022-10-31 | NA | NA | 10 kgs | 0 | - | - | 11600 |  | 0 | 0 | 0 | Venue
36 | HOTC | Photo & Video | Mr | Sumer | Bhati | 1 | Trident | Double Occupancy | 2022-10-27 | 2022-10-31 |  | 1 | 1 | 1 | 1 |  | DEL-UDR | Eco | 2022-10-27 | UK 627 | 14:45 | UDR-DEL | 2022-10-31 | AI 472 | 15:05 | 10 kgs | 4 | 16500 | 66000 | 10950 |  | 0 | 0 | 0 | Venue
37 | HOTC | Photo & Video | Mr | Sovan | Biswas | 0 | Trident | Double Occupancy | 2022-10-27 | 2022-10-31 | [6 empty] | CCU-DEL-UDR | Eco | 2022-10-27 | 6E 358 6E 6264 | 18:50 | UDR-DEL-CCU | 2022-10-31 | 6E 6789 6E 912 | 12:45 | 10 kgs | 0 | - | - | 33223 |  | 0 | 0 | 0 | Venue
38 | HOTC | Photo & Video | Mr | Humayun | Khan |  |  | - | [18 empty] | 0 |  |  | 6300 | Cancelation both ways |  | 0 | 0
39 | DJ | DJ | Mr | Amit | Mayavansi | 1 | Hibiscus | Double Occupancy | 2022-10-28 | 2022-10-31 |  |  | 1 | 1 | 1 |  | BOM-UDR | Eco | 2022-10-28 | UK 613 | 13:45 | UDR-BOM | 2022-10-31 | UK 614 | 14:20 |  | 3 | 4400 | 13200 | 16970 |  | 0 | 0 | 0 | Venue
40 | DJ Asst | DJ Asst | Mr | Sumit | Shenoy | 0 | Hibiscus | Double Occupancy | 2022-10-28 | 2022-10-31 | [6 empty] | BOM-UDR | Eco | 2022-10-28 | UK 613 | 13:45 | UDR-BOM | 2022-10-31 | UK 614 | 14:20 |  | 0 | - |  | 20106 |  | 0 | 0 | 0 | Venue
41 | Team Gurdeep | Singer | Mr | Gurdeep | Mehendi | 1 | Trident | Suite | 2022-10-28 | 2022-10-29 |  |  | 1 |  |  |  | BOM-UDR | BIZ | 2022-10-28 | UK 613 | 13:45 | UDR-BOM | 2022-10-29 | UK 614 | 14:20 | - | 1 | 42275 | 42275 | 47800 |  | 0 | 0 | 0 | Room Service
42 | Team Gurdeep | Manager | Mr | Jaspreet | Singh | 1 | Trident | Double Occupancy | 2022-10-28 | 2022-10-29 |  |  | 1 |  |  |  | IXC-UDR | PreEco | 2022-10-28 | UK 654, UK 613 | 13:45 | IXC-UDR | 2022-10-29 | UK 614, UK 651 | 14:20 | - | 1 | 16500 | 16500 | 44745 |  | 0 | 0 | 0 | Room Service
43 | Team Gurdeep | Band Members | Mr | Jayesh | Ashar | 0 | Trident | Double Occupancy | 2022-10-28 | 2022-10-29 | [6 empty] | BOM-UDR | PreEco | 2022-10-28 | UK 613 | 13:45 | UDR-BOM | 2022-10-29 | UK 614 | 14:20 | - | 0 | - | - | 24750 |  | 0 | 0 | 0 | Room Service
44 | Team Gurdeep | Band Members | Mr | Amrut | Palekar | 1 | Trident | Double Occupancy | 2022-10-28 | 2022-10-29 |  |  | 1 |  |  |  | BOM-UDR | PreEco | 2022-10-28 | UK 613 | 13:45 | UDR-BOM | 2022-10-29 | 6E 5249 | 8:30 | 30 KG Extra | 1 | 16500 | 16500 | 41650 |  | 0 | 0 | 0 | Room Service
45 | Team Gurdeep | Band Members | Mr | Rushikesh | Gurav | 0 | Trident | Double Occupancy | 2022-10-28 | 2022-10-29 | [6 empty] | BOM-UDR | PreEco | 2022-10-28 | UK 613 | 13:45 | UDR-BOM | 2022-10-29 | 6E 5249 | 8:30 | 1 Bag Extra | 0 | - | - | 15550 |  | 0 | 0 | 0 | Room Service
46 | Team Gurdeep | Band Members | Mr | Ahmed | khawra | 1 | Trident | Double Occupancy | 2022-10-28 | 2022-10-29 |  |  | 1 |  |  |  | BOM-UDR | PreEco | 2022-10-28 | UK 613 | 13:45 | UDR-BOM | 2022-10-29 | 6E 5249 | 8:30 | 20 KG Extra | 1 | 16500 | 16500 | 32650 |  | 0 | 0 | 0 | Room Service
47 | Team Gurdeep | Band Members | Mr | Mayur | thombre | 0 | Trident | Double Occupancy | 2022-10-28 | 2022-10-29 | [6 empty] | BOM-UDR | PreEco | 2022-10-28 | UK 613 | 13:45 | UDR-BOM | 2022-10-29 | 6E 5249 | 8:30 | 1 Bag extra | 0 | - | - | 15550 |  | 0 | 0 | 0 | Room Service
48 | Team Gurdeep | Band Members | Mr | Somen | Sarkar | 1 | Trident | Double Occupancy | 2022-10-28 | 2022-10-29 |  |  | 1 |  |  |  | BOM-UDR | PreEco | 2022-10-28 | UK 613 | 13:45 | UDR-BOM | 2022-10-29 | 6E 5249 | 8:30 | 1 Bag extra | 1 | 16500 | 16500 | 15550 |  | 0 | 0 | 0 | Room Service
49 | Team Gurdeep | Band Members | Mr | Tajinder | Singh | 0 | Trident | Double Occupancy | 2022-10-28 | 2022-10-29 | [6 empty] | BOM-UDR | PreEco | 2022-10-28 | UK 613 | 13:45 | UDR-BOM | 2022-10-29 | 6E 5249 | 8:30 | 1 Bag extra | 0 | - | - | 15550 |  | 0 | 0 | 0 | Room Service
50 | Team Gurdeep | Band Members | Mr | Yash | chauhan | 1 | Trident | Double Occupancy | 2022-10-28 | 2022-10-29 |  |  | 1 |  |  |  | BOM-UDR | PreEco | 2022-10-28 | UK 613 | 13:45 | UDR-BOM | 2022-10-29 | 6E 5249 | 8:30 | 1 Bag extra | 1 | 16500 | 16500 | 15550 |  | 0 | 0 | 0 | Room Service
51 | Team Gurdeep | Band Members | Mr | Prasad | Satam | 0 | Trident | Double Occupancy | 2022-10-28 | 2022-10-29 | [6 empty] | BOM-UDR | PreEco | 2022-10-28 | UK 613 | 13:45 | UDR-BOM | 2022-10-29 | 6E 5249 | 8:30 | 1 Bag extra | 0 | - | - | 15550 |  | 0 | 0 | 0 | Room Service
52 | Team Salman Ali | Singer | Mr | Salman | Ali | 1 | Trident | Suite | 2022-10-29 | 2022-10-30 |  |  |  | 1 |  |  | GAU-DEL-UDR | 1st Row | 2022-10-29 | 6E 6329 , UK 627 | 14:45 | UDR-BOM | 2022-10-30 | 6E 5346 | 7:20 |  | 1 | 42275 | 42275 | 23721 |  | 0 | 0 | 0 | Venue
53 | Team Salman Ali | Brother | Mr | Shameem | Khan | 0 | Trident | Double Occupancy | 2022-10-29 | 2022-10-30 | [6 empty] | GAU-DEL-UDR | 1st Row | 2022-10-29 | 6E 6329 , UK 627 | 14:45 | UDR-DEL | 2022-10-30 | 6E 2092 | 7:55 |  | 0 | - | - | 23721 |  | 0 | 0 | 0 | Venue
54 | Team Salman Ali | Musicians | Mr | Afzal | Ahmad | 1 | Trident | Double Occupancy | 2022-10-29 | 2022-10-30 |  |  |  | 1 |  |  | GAU-DEL-UDR | Eco | 2022-10-29 | 6E 6329 , UK 627 | 14:45 | UDR-DEL | 2022-10-30 | 6E 2092 | 7:55 |  | 1 | 16500 | 16500 | 21721 |  | 0 | 0 | 0 | Venue
55 | Team Salman Ali | Musicians | Mr | Madhukar |  | 0 | Trident | Double Occupancy | 2022-10-29 | 2022-10-30 | [6 empty] | GAU-DEL-UDR | Eco | 2022-10-29 | 6E 6329 , UK 627 | 14:45 | UDR-DEL | 2022-10-30 | 6E 2092 | 7:55 |  | 0 | - | - | 21721 |  | 0 | 0 | 0 | Venue
56 | Team Salman Ali | Musicians | Mr | Shankar | Lama | 1 | Trident | Double Occupancy | 2022-10-29 | 2022-10-30 |  |  |  | 1 |  |  | DEL-UDR | Eco | 2022-10-29 | 6E 6019 | 8:15 | UDR-DEL | 2022-10-30 | 6E 2092 | 7:55 |  | 1 | 16500 | 16500 | 14241 |  | 0 | 0 | 0 | Venue
57 | Team Salman Ali | Musicians | Mr | Mohd | Asharaf | 0 | Trident | Double Occupancy | 2022-10-29 | 2022-10-30 | [6 empty] | DEL-UDR | Eco | 2022-10-29 | 6E 6019 | 8:15 | UDR-DEL | 2022-10-30 | 6E 2092 | 7:55 |  | 0 | - | - | 14241 |  | 0 | 0 | 0 | Venue
58 | Team Salman Ali | Musicians | Mr | Deepak | Anand | 1 | Trident | Double Occupancy | 2022-10-29 | 2022-10-30 |  |  |  | 1 |  |  | DEL-UDR | Eco | 2022-10-29 | 6E 6019 | 8:15 | UDR-DEL | 2022-10-30 | 6E 2092 | 7:55 |  | 1 | 16500 | 16500 | 14241 |  | 0 | 0 | 0 | Venue
59 | Team Salman Ali | Musicians | Mr | Shabbu |  | 0 | Trident | Double Occupancy | 2022-10-29 | 2022-10-30 | [6 empty] | DEL-UDR | Eco | 2022-10-29 | 6E 6019 | 8:15 | UDR-DEL | 2022-10-30 | 6E 2092 | 7:55 |  | 0 | - | - | 14241 |  | 0 | 0 | 0 | Venue
60 | Team Salman Ali | Manager | Mr | Sumit | Behal | 1 | Trident | Double Occupancy | 2022-10-29 | 2022-10-30 |  |  |  | 1 |  |  | DEL-UDR | Eco | 2022-10-29 | 6E 6019 | 8:15 | UDR-DEL | 2022-10-30 | 6E 2092 | 7:55 |  | 1 | 16500 | 16500 | 14241 |  | 0 | 0 | 0 | Venue
61 | Team Salman Ali | Sound Engineer | Mr | Nazir | Mohammad Malik | 0 | Trident | Double Occupancy | 2022-10-29 | 2022-10-30 | [6 empty] | Vadodara -UDR | Self Drive | 2022-10-29 | Self Drive | Self Drive | UDR-Vadodara | 2022-10-30 | Self Drive | Self Drive |  | 0 | - | - | 0 |  | 0 | 0 | 0 | Venue
62 | Bridal Hair | Hairstylist | Ms. | Aayesha (Ritika) | Mulla | 1 | Leela | Double Occupancy | 2022-10-28 | 2022-10-31 |  |  | 1 | 1 | 1 |  | BOM-UDR | Eco | 2022-10-28 | UK 613 | 13:45 | UDR-BOM | 2022-10-31 | UK 614 | 14:20 | 20kg | 3 | Leela | 0 | 77348 | 54000 baggage | 0 | 0 | 0 | Venue
63 | Bridal Hair | Asst | Ms. | Varsha | Mandlekar | 0 | Leela | Double Occupancy | 2022-10-28 | 2022-10-31 | [6 empty] | BOM-UDR | Eco | 2022-10-28 | UK 613 | 13:45 | UDR-BOM | 2022-10-31 | UK 614 | 14:20 | 30 kg | 0 | Leela | Leela | 23348 |  | 0 | 0 | 0 | Per Diem
64 | Panditji | Pandit Ji | Mr | Harsh | Saraswat | 1 | Hibiscus | Double Occupancy | 2022-10-29 | 2022-10-31 |  |  |  | 1 | 1 |  | BOM-UDR | Eco | 2022-10-29 | 6E 6107 | 19:00 | UDR-BOM | 2022-10-31 | UK 614 | 14:20 |  | 2 | 4400 | 8800 | 14300 |  | 2500 | 2 | 5000 | Per Diem
65 | Panditji | Pandit Ji | Mr | Anand | Oza | 0 | Hibiscus | Double Occupancy | 2022-10-29 | 2022-10-31 | [6 empty] | BOM-UDR | Eco | 2022-10-29 | 6E 6107 | 19:00 | UDR-BOM | 2022-10-31 | UK 614 | 14:20 |  | 0 | - |  | 14300 |  | 2500 | 2 | 5000 | Per Diem
66 | Bridal make up | Makeup artist | Ms | Meera | Sakhrani | 1 | Leela | Double Occupancy | 2022-10-28 | 2022-10-31 |  |  | 1 | 1 | 1 |  | JAI-UDR | Eco | 2022-10-28 | 6E 811 | 14:55 | UDR-DEL | 2022-10-31 | 6E 115 | 9:00 | 5 kg | 3 | Leela | 0 | 14133 | 4500 Extra luggage added | 0 | 0 | 0 | Venue
67 | Bridal make up | Asst | Ms | Anchal | Sakhrani | 0 | Leela | Double Occupancy | 2022-10-28 | 2022-10-31 | [6 empty] | JAI-UDR | Eco | 2022-10-28 | 6E 811 | 14:55 | UDR-DEL | 2022-10-31 | 6E 115 | 9:00 |  | 0 | Leela | Leela | 9633 |  | 0 | 0 | 0 | Per Diem
68 | Bridal make up | Asst | Ms | Kumari | Usha | 1 | Hibiscus | Twin Bed | 2022-10-28 | 2022-10-31 |  |  | 1 | 1 | 1 |  | JAI-UDR | Eco | 2022-10-28 | 6E 811 | 14:55 | UDR-DEL | 2022-10-31 | 6E 115 | 9:00 |  | 3 | 4400 | 13200 | 9633 |  | 2500 | 3 | 7500 | Per Diem
69 | Bridal make up | Makeup artist | Ms | Tripti | Rastogi | 1 | Trident | Double Occupancy | 2022-10-27 | 2022-10-31 |  | 1 | 0 | 0 | 0 | 0 | DEL-UDR | Eco | 2022-10-27 | AI 471 | 14:35 | UDR-DEL | 2022-10-31 | AI 472 | 15:05 |  | 1 | 16500 | 16500 | 11908 |  | 2500 | 4 | 10000 | Per Diem
70 | Bridal make up | Asst | Ms | Rashmi | - | 0 | Trident | Double Occupancy | 2022-10-28 | 2022-10-31 | [6 empty] | DEL-UDR | Eco | 2022-10-28 | 6E 6019 | 8:15 | UDR-DEL | 2022-10-31 | 6E 6265 | 19:20 |  | 0 | - | - | 12164 |  | 2500 | 4 | 10000 | Per Diem
71 | Mrs. Sangwan HMU | Makeup artist | Ms | Taruna | Vashishth | 1 | Hibiscus | Double Occupancy | 2022-10-26 | 2022-10-31 | 1 | 1 | 1 | 1 | 1 |  | DEL-UDR | Drive | 2022-10-26 | Drive | Drive | UDR-DEL | 2022-10-31 | Drive | Drive |  | 5 | 4400 | 22000 | 0 |  | 2500 | 5 | 12500 | Per Diem
74 | Mrs. Sangwan HMU | Makeup artist | Mr | Akshay | Vashishth | 0 | Hibiscus | Double Occupancy | 2022-10-26 | 2022-10-31 | [6 empty] | DEL-UDR | Drive | 2022-10-26 | Drive | Drive | UDR-DEL | 2022-10-31 | Drive | Drive |  | 5 | 4400 | 22000 | 0 |  | 2500 | 5 | 12500 | Per Diem
72 | Mrs. Sangwan HMU | Makeup artist | Mr | Rohit | Kumar | 1 | Hibiscus | Double Occupancy | 2022-10-27 | 2022-10-31 | [6 empty] | DEL-UDR | Drive | 2022-10-27 | Train | 10:45 | UDR-DEL | 2022-10-31 | Drive | Drive |  | 4 | 4400 | 17600 | 0 |  | 2500 | 4 | 10000 | Per Diem
73 | Mrs. Sangwan HMU | Makeup artist | Mr | Anil | - | 0 | Hibiscus | Double Occupancy | 2022-10-27 | 2022-10-31 |  | 1 | 1 | 1 | 1 |  | DEL-UDR | Drive | 2022-10-27 | Train | 10:45 | UDR-DEL | 2022-10-31 | Drive | Drive |  | 0 | - |  | 0 |  | 2500 | 4 | 10000 | Per Diem
75 | Mrs. Sangwan HMU | Saree drapper | Ms | Priyanka |  | 1 | Hibiscus | Double Occupancy | 2022-10-27 | 2022-10-31 |  | 1 | 1 | 1 | 1 |  | DEL-UDR | Drive | 2022-10-27 | Train | 10:45 | UDR-DEL | 2022-10-31 | Drive | Drive |  | 0 | - |  | 0 |  | 2500 | 4 | 10000 | Per Diem
82 | Shadow | Mrs Sangwan | Ms | Cheryl | Local | 0 | Hibiscus | Double Occupancy | 2022-10-27 | 2022-10-31 | [6 empty] | Local | Local | 2022-10-27 | Local | Local | Local | Local | Local | Local |  | 4 | TBC | 0 | 0 |  | 2500 | 4 | 10000 | Per Diem
76 | Wedding Musician | Wedding Musician | Mr | Solanki | Manishkumar Arvindbhai | 1 | Hibiscus | Tripple occupancy | 2022-10-30 | 2022-10-31 |  |  |  |  | 1 |  | BOM-UDR | Eco | 2022-10-30 | UK 613 | 13:45 | UDR-BOM | 2022-10-31 | UK 614 | 14:20 |  | 1 | 4400 | 4400 | 21238 | One way cancelation | 2500 | 1 | 2500 | Per Diem
77 | Wedding Musician | Wedding Musician | Mr | Deven | Pravinkumar Pandya | 0 | Hibiscus | Tripple occupancy | 2022-10-30 | 2022-10-31 | [6 empty] | BOM-UDR | Eco | 2022-10-30 | UK 613 | 13:45 | UDR-BOM | 2022-10-31 | UK 614 | 14:20 |  | 0 | - |  | 21238 | One way cancelation | 2500 | 1 | 2500 | Per Diem
78 | Wedding Musician | Wedding Musician | Mr | Ganesh | Prakash Sawant | 0 | Hibiscus | Tripple occupancy | 2022-10-30 | 2022-10-31 | [6 empty] | BOM-UDR | Eco | 2022-10-30 | UK 613 | 13:45 | UDR-BOM | 2022-10-31 | UK 614 | 14:20 |  | 0 | - |  | 21238 | One way cancelation | 2500 | 1 | 2500 | Per Diem
79 | Wedding Musician | Wedding Musician | Ms | Bijal | Kamlesh Parekh | 0 | Hibiscus | Twin Bed | 2022-10-30 | 2022-10-31 | [6 empty] | BOM-UDR | Eco | 2022-10-30 | UK 613 | 13:45 | UDR-BOM | 2022-10-31 | UK 614 | 14:20 |  | 0 | - |  | 21238 | One way cancelation | 2500 | 1 | 2500 | Per Diem
80 | Wedding Musician | Wedding Musician | Mr | Neeraj | Balchandra Lele | 1 | Hibiscus | Double Occupancy | 2022-10-30 | 2022-10-31 |  |  |  |  | 1 |  | BOM-UDR | Eco | 2022-10-30 | UK 613 | 13:45 | UDR-BOM | 2022-10-31 | UK 614 | 14:20 |  | 1 | 4400 | 4400 | 21238 | One way cancelation | 2500 | 1 | 2500 | Per Diem
81 | Wedding Musician | Wedding Musician | Mr | Vijay | Belbanshi | 0 | Hibiscus | Double Occupancy | 2022-10-30 | 2022-10-31 | [6 empty] | BOM-UDR | Eco | 2022-10-30 | UK 613 | 13:45 | UDR-BOM | 2022-10-31 | UK 614 | 14:20 |  | 0 | - |  | 21238 | One way cancelation | 2500 | 1 | 2500 | Per Diem
83 | Choreographer | Choreo Asst | Ms | Soochana | Sudesh Chorge | 1 | Hibiscus | Single Occupancy | 2022-10-27 | 2022-10-29 | 0 | 1 | 1 | 0 |  |  | BOM-UDR | Self | 2022-10-27 | UK 613 | 13:45 | UDR-BOM | 2022-10-29 | UK 614 | 14:20 |  | 2 | 4400 | 8800 | 0 |  | 2500 | 3 | 7500 | Per Diem
1599710
84 | Rupa Bhinjiyani | Guest | Guest | Guest | Guest | 1 | Trident | Single Occupancy | 2022-10-27 | 2022-10-28 |  | 1 | [20 empty] | 0
85 | Rupa Bhinjiyani | Guest | Guest | Guest | Guest | 1 | Trident | Single Occupancy | 2022-10-27 | 2022-10-28 |  | 1 | [20 empty] | 0
86 | Bridal mehendi | For Janki | Ms | Sona | Mishra | Drive | Wash & Change Room | Wash & Change Room | 2022-10-28 | 2022-10-28 | [7 empty] | Eco | 2022-10-28 | [12 empty] | 2500 | 1 | 2500
87 | Bridal mehendi | For Immediate family | Ms | Girl | 1 | Drive | Wash & Change Room | Wash & Change Room | 2022-10-28 | 2022-10-28 | [8 empty] | 2022-10-28 | [12 empty] | 2500 | 1 | 2500
88 | Bridal mehendi | For Immediate family | Ms | Girl | 2 | Drive | Wash & Change Room | Wash & Change Room | 2022-10-28 | 2022-10-28 | [8 empty] | 2022-10-28 | [12 empty] | 2500 | 1 | 2500
89 | Bridal mehendi | For Immediate family | Ms | Girl | 3 | Drive | Wash & Change Room | Wash & Change Room | 2022-10-28 | 2022-10-28 | [8 empty] | 2022-10-28 | [12 empty] | 2500 | 1 | 2500
[11 empty] | 10 | 23 | 33 | 32 | 29 | 3 | [12 empty] | 1178050 |  |  |  | 165 | 412500
90 | Hamper Boys |  |  |  |  | Local |  |  | 2022-10-27 | 2022-10-30 | [8 empty] | 2022-10-27
91 | Hamper Boys |  |  |  |  | Local |  |  | 2022-10-27 | 2022-10-30 | [8 empty] | 2022-10-27
92 | Salon Girl |  |  |  |  | Local |  |  | 2022-10-27 | 2022-10-30 | [8 empty] | 2022-10-27
Formulas:
Check in date = [Arrival Date]
Departure Date = [Check out date]
Arrival Date = [Check in date]

## Aug 29 recce
Sr No | Salutation | First Name | Second Name | Sector | Date | Flight No | Dep Time | Date | Sector | Flight No | Dep Time
1 | Ms | Monalisa | Phillips | BOM-UDR | 2022-08-29 | AI 643 | 14:20 hrs | 2022-08-31 | UDR-BOM | AI 644 | 16:30
2 | Mr | Saival | Jaradi | BOM-UDR | 2022-08-29 | AI 643 | 14:20 hrs | 2022-08-31 | UDR-BOM | AI 644 | 16:30
3 | Ms | Heena Anisa | Kapoor | DEL-UDR | 2022-08-30 | 6E 6019 | 07:15 hrs | 2022-08-30 | UDR-DEL | 6E 6265 | 19:20
4 | Mr | Arun | Rawat | DEL-UDR | 2022-08-30 | 6E 6019 | 07:15 hrs | 2022-08-30 | UDR-DEL | 6E 6265 | 19:20
5 | Mr | Surinder | Sharma | DEL-UDR | 2022-08-30 | 6E 6019 | 07:15 hrs | 2022-08-30 | UDR-DEL | 6E 6265 | 19:20
6 | Ms | Iris | Tung | BOM-UDR | 2022-08-30 | 6E 5378 | 17:50 hrs | 2022-08-31 | UDR-BOM | AI 644 | 16:30

## Aug 29 Recce Agenda
Wedding Celebrations of Janki & Rahul
Recce Agenda - Aug 29 to 31, 2022
Event Dates |  | Oct 27 to 30, 2022
Attendees |  | Rahul, Mrs Sangwan, Janki, Radhika, Anisa, Monalisa, Iris & Saival
2022-08-29 | Time
| 16:30 hrs | Family checks in at Leela
| 17:30 hrs | Mona & Saival reach Raas Leela
| 18:00 to 20:00 hrs | Rooming Allocation with Family, Hotel & Mona
| 20:00 hrs | Dinner - Food Tasting with Leela
2022-08-30 | 07:55 hrs | Anisa + Team land into Udaipur
| 10:00 hrs to 11:00 hrs | Anisa + Team take measurements at Leela
| 11:00 hrs to 13:00 hrs | Venue walkthrough on decor aspects - Family+Anisa+Saival
| 13:00 to 14:30 hrs | Lunch Food Tasting
| 15:30 to 17:30 hrs | Final decor element sheet presentation & signoff on the decor sheet - Family+Anisa+ME
| 17:30 hrs to 18:30 hrs | Family + Saival & Mona visit Jagmandir for recce & closing on Final Menus
| 19:00 to 20:00 hrs | Pending Pointers with Hotel
| 20:00 to 21:30 hrs | Dinner - Food Tasting with Leela & Iris arrives at Leela
2022-08-31 | 10:00 to 13:30 hrs | J&R + MEW close on the final menus & pending hospitality pointers
| 14:00 hrs | MEW to leave for airport
Family to leave for airport

## MoM July 12
Wedding Celebrations of Janki & Rahul
Minutes of Meeting - July 12, 2022
Event Dates | Oct 27 to 30, 2022
Attendees | Rahul, Janki & Saival
DISCUSSION POINTERS
Oct 28 Jagmandir Menu - Saival to check on options for soup, more options on Main Course. Buffet will be laid outside the existing restaurant along with guest stitting. Saival to check for Food Tasting during recce
HOTC - Zoe to check with HOTC for the videos as per last call on July 3 call
DJ Amit - Zoe to check with DJ Amit on his performance fees of 75k
Hair Salon - Iris to speak with Hair Salon team for revised cost
Hampers - Iris to share Hamper Cost for the items selected by Janki
Crew TLB - Saival to update on the updated Crew TLB sheet & air travel details
Mehendi Ancilarry Artists - Lak Bangles has been confirmed. MEW to share cost of Caricature Artist & Parrot Card Reader
Wedding Reception - MEW to share options for Pianist (Pianist to play melodic, slow, popular bolly songs, American Songs along with Karaoke
August Recce - Aug 30 has been decided as recce date for Udaipur
Service Charge - MEW to speak with Leela on the 2% service charge levied
Itinerary

## MoM July 21
Wedding Celebrations of Janki & Rahul
Minutes of Meeting - July 21, 2022
Event Dates | Oct 27 to 30, 2022
Attendees | Janki, Iris, Mona
DISCUSSION POINTERS
All day Lounge : Hotel is offering the Library Bar at Rs. 50,000/- plus taxes (tea, coffee,cookies). Iris to inform hotel to add Masala chai.
Reccee Rates: Hotel offering 20% discount on room tariff( bar rates)
Artist Room: To see further discounted rates at Trident for Deluxe Garden view room and Suites for Gurdeep Mehendi, Salman Ali.
HOTC - Zoe to check with HOTC if they are giving raw footages to Janki.
Cricket Match Tshirt: Have to share cricket match tshirt pictures with Janki for reference.
Hair Salon - Have to find out the fees of Make up artist Guru from Delhi for Janki's mom and Kaki
Hair and makeup: Iris to schedule a concall with Janki, Meera and Ritika
Hampers - Iris to share Hamper Cost for the items selected by Janki
Menu: Janki and Rahul to check the menu and give a feedback by 28th July. Iris to send the Menu again.
Trident rooms: To find free cancellable rooms tariff with Trident.
Mehendi Decor: To suggest what can be done for Janki's mehendi during the Cricket match.
Wheelchair for travel: Wheelchair in Innova for Nathdwara Darshan on 27th.
26th family Arrival: Janki+13 guests arriving on 26th. Names upadted.
Guruji's arrangements: Guruji's food and refreshments to be made only with Gangajal. Also Guruji will require a special dedicated place where there is no alocohol or non veg.
Food Placement: Non veg counters to be placed away from Veg buffet.
HAMPERS POINTERS
Hamper: Finalisation to be done by Janki
Potlis: Janki to finalise on the thank you gift potlis.
HOSPITALITY POINTERS
Communication Timeline: Iris to share the timeline of guest communication with Janki
Visa communication: Separate message for Visa to be sent to the guests. Janki to reconfirm.
Salon communication: Team to share two options of messages with Janki with for salon one where guests have to pay for services and one complimetary.
RahulkiJaan: The name for communication to be changed to "RahulkiJaan". Janki to reconfirm.
RSVP: To message Keiky Press and reconfirm his arrival and departure dates.
Extra beds: 8 extra beds are confirmed by the hotel. Iris to find out if they can provide mattresses and if yes then at what cost.
Baby Cot: Only 2 baby cot available by the hotel. Janki to reconfirm with Rahul the final numbers.

## MoM Aug 29
Wedding Celebrations of Janki & Rahul
Minutes of Meeting - Aug 29, 2022
Event Dates | Oct 27 to 30, 2022
Attendees | Janki, Rahul, Mr. Sangwan, Mrs. Sangwan, Iris, Saival, Mona
Hospitality | Room Allocations for guest stay to be finalised by end of September
All day lounge confirmed at INR 50,000 for 29th Oct. Awaiting price for 28th Oct.
Ironing package to be removed from all. Hotel to advise package for family.
10 extra beds in all
Hampers to be done by Janki's sister.
Gifting to be done by Janki's family.
Mrs Sangwan to advise on the sweets for her side of the family from JMB.
Family to leave for Nathdwara
On 26th Oct for Nathdwara visit total pax count 15-18. MEW to finalise the travel plan with 2 wheelchairs and attendant at disposal until return .
Direct payment room updates given to families.
The final pricing for family local hair stylist is INR 1,75,000 for 6 people for hair and saree. (only for 28th, 29th, 30th Oct)
Entertainment | Inner courtyard hotel entertainment every evening. Time to be decided
Saafa to be finalised
Space for dance practice to be advised
29th Oct Dhol wala for Bhat to be suggested to the family and dholki
Cricket jersey material to be dry fit. Design to be finalised by Parul
Floats for pool party
Permission for volley ball at the pool
28th family at 1 pm for 6 people (Janki, Radhika, Mrs Bhimjiyani, Kaki , Mrs Sangwan and Parul)
27th Oct welcome dinner at Promenade at Udaivilas to be confirmed by Saival (no. of pax to be advised by family)
Sehnai wala suggestion to be given to Mrs Sangwan
1 Thal with diya to be arranged with a small idol of Ganeshji for the Ganesh Pooja.
Food and Beverage | Final revised menu awaited from the hotel
Italian food not good enough is family feedback
For pool party beer and soft beverage to be served in disposable glasses. MEW to source glasses.
1 sweets box at pheras (1/2 kg)
1 sweets box during engagement. (1 kg)
Events | Oct 27 - Engagement ceremony in the royal suite. Mrs Sangwan to advise any further arrangements
Mrs Sangwan to advise if a pandit is required for the engagement. If yes local pandit to be arranged by MEW.
Oct 30 - Pooja for Rahul in the morning (Venue - Suite)
Oct 30 - Ganesh Staphna & Mandvo in the inner courtyard 09:00 to 10:30 hrs0
Muh dikhai ceremony at Maharaja Suite on 30th
Decor | Milni haar to be mogra flowers 2 layers (quantity to be advised by Mrs Sangwan)
Jai mala pictures to be shared with Mrs Sangwan
2 chokis to be placed in Rahuls room for any kind of Pooja
Others | 3 Rooms for Mrs Sangwan HMU from Delhi - Awaiting dates.

## MoM SEP 16
Wedding Celebrations of Janki & Rahul
Minutes of Meeting - September, 2022
Event Dates | Oct 27 to 30, 2022
Attendees | Zoe, Saival, Iris, Monalisa, Heena, Alekha
Hospitality | Welcome hampers & Thank you gifts done by Janki's sister.
Assembly of hampers may be teams responsibility, and beautification role needs to be discussed with Janki
Second shadow needs to be decided
Shadow tickets need to be booked
Guests outside Leela- needs to be checked if they are doing their own arrangements or do cars need to be organised at their disposable
Anisa will stay at the Leela 27th onwards
As per Rahul's confirmation Aditya will be staying at Leela from 28th
2 rooms blocked at Leela for (Yash/Neera and Rahul/Parul) - Guest to move to their actual room on 27th
Karanbir Sirohi has confrimed that he is arriving on the 27th
Entertainment | Logo has been actioned with Ichha- Rahul to be informed
Food and Beverage | Room service cap needs to be discussed with Janki for Anisa & Rajat at the Leela
Photo & Video team, and DJ & Assistant will be eating at the events at Leela
Crew meals- where & what they eat is pending
Crew meals- Ala Carte from the hotel with a limited discounted menu as all crew will not get a chance to eat at Raas Leela twice per day as our itinerary is super packed all day each day
27th Dinner menu shared, the same needs to be finalised.
Events | Photoshoot on the 27th is confirmed - Rahul to be informed
Photographers need to confirm the location of shoot & interview timings
Banquet hall can be used- but Rahul needs to inform team what time they will use it
28th pool gathering has a boom box
Client to either provide a playlist of choice, or DJ Amit to give 1 Hindi & 1 English playlist
Photographers will be present at the pool gathering- Rahul to be informed
27th Drinks at UDV promenade, followed by Dinner at 7:30pm- Rahul to be informed
No entertainment on the 27th Dinner, hotel will provide all decor
Cricket- local vendor is providing all ancillary items- Rahul to be informed
Cricket- no rules are being printed, umpire will go through all the rules verbally- Rahul to be informed
Mewar has a bar, but no afterparty food- Rahul to be informed
Pyjama party to be continued separately in suites- Rahul to be informed
Haldi location is inner courtyard, provided it starts at 10:30am, if not a new place to be decided- Rahul to be informed
Sehra Bandi location is poolside for boys & library bar for girls- Rahul to be informed
Baraat car- discussion with Rahul
Decor | Anisa needs to send list to Saival for Mehendi decor- additional cost by hotel may be possible

## Sheet16
Rooming
Book 2 rooms at Leela for 26th for Sangwans (Yash/Neera and Rahul/Parul)
Janki has 5 extra rooms booked at Trident for 28-31. Based on current count, these are not required unless we need to hold any back for vendors or others (deadline is Sep 27 to cancel)?
Please confirm when Karanbir Sirohi has said he is arriving. We need to sort out a room at Trident for him on 27th
We currently have 3 rooms at Leela for the 2 make-up artists and Aditya (is Aditya arriving on the 27th or the 28th?)
Where are we putting Anisa?
Confirm all remaining vendor rooming situation
Food
Can we agree on an UDV menu? Mix of Italian and Indian
Cocktail list / menu from bartender for each event
Re: lounge - confirmed for 28th only (not on 29th or 30th)
Other
What is cost of safas?
Remaining workstreams for Ittcha
- Has JR Logo been designed?
Are the Leela flutists playing in the mornings?
Walk through show flow in detail and confirm outstandings for all events
- 27th: photo shoot (is it happening?), dance practice (reserve times in banquet hall), interviews HOTC, what time is dinner, are we doing drinks beforehand, is there any entertainment at dinner
- 28th: what is music arrangement for pool gathering, is there a photo shoot?, has JR logo stencil been actioned
- 29th: cricket (discuss all ancillaries - score board, commentator, umpire, printing rules/teams for spectators), location for PJ party confirmed as Marwar Hall
- 30th: what is haldi location?, what is sehra bandhi location?, has baraat car been sorted?, cocktail receptoin on terrace, we need to break guests into groups for photos

## MoM Sept 20
Wedding Celebrations of Janki & Rahul
Minutes of Meeting - September 20, 2022
Event Dates | Oct 27 to 30, 2022
Attendees | Saival, Iris, Monalisa, Heena, Alekha, Natasha, Dhruv
Hospitality | Welcome hampers & Thank you gifts done by Janki's sister. Mona to connect to Kajal for same.
Janki to inform if 3 shadows are required. Iris to revert with the tickets and stay if three are considered.
Itinerary to be placed with the hampers.
Hampers to reach Leela on 26th evening.
4 Leela crew rooms form 28th to 31st : Aditya Motwane, Anisa, Meera, Ritika. (IRD will have a cap as discussed)
Meera to revert with the final discussion with travel dates and number of people traveling along.
Meera has to share her schedule with Janki of getting ready.
Janki and Rahul have to share the room allocations.
Rahul Janki to do suite allocation for 27th
Total extra beds provided by the hotel 12 no.'s
Janki to identify family rooms for special billing instructions.
Mrs Sangwan and Mrs Bhimjiyani will identify rooms for thank you gifts drops
Entertainment | Poolside boombox to play premixed playlist by DJ on Mehendi
Iris to check if 27th photoshoot can be rescheduled.
Dance practice schedule for 27th and 28th
Saival to suggest fun prices for the cricket match
Cricket rules will be announced by the Umpire.
Dhol wala required for Bhat, Sehrabandi, and grahapravesh and ghod chadi
Flutist during breakfast.
Janki to advise songs for entry.
Janki to identify the family member who will compare the sangeet and reception.
Food and Beverage | Room service cap needs to be discussed with Janki for Anisa & Rajat at the Leela
Photo & Video team, and DJ & Assistant will be eating at the events at Leela
Crew meals need to finalise
Team to share vendor meals plan with Janki.
Awaiting limited menu from Leela for Dining room for Photo team
27th Dinner menu shared, the same needs to be finalised.
Revised costing of alcohol awaited from Leela
Final menu from Leela awaited.
Poolside only to have small bar with beer and soft beverages served in dispoable glasses.
Janki to be served food ar poolside.
29th after party food cancelled.
Events | Photographers need to confirm the location of shoot & interview timings
DJ Amit to give 1 Hindi & 1 English playlist for poolside.
Haldi location is inner courtyard, provided it starts at 10:30am
Place for Bhat to be suggested
Local panditji required on 27th engagement ceremony.
27th Itinerary has to be made and shared.
Cricket jersey finalisation

## Hotel Inspection Checklist
HOTEL CHECKLIST
Sr. No. | Type | Particulars | Specification | Hotel Remarks | MEW Remarks
1 | CONTACT | Overall Contact Person from Hotel | ANIKET
Front Office Manager Contact
Duty Manager / Rooming List Contact
|  | Food & Beverage Contact | AMIT
House Keeping
2 | TOTAL INVENTORY AND DIFFERENT CATEGORY ROOM | Total Inventory | 80 rooms
|  | Rooms | 72
|  | Suites | 8
|  | No. of Floors | 3
|  | No. of Extra Beds Available | 10
|  | Total no. Wheel Chair at the Hotel | 2
|  | No. of Physically Challenged Room | 1
|  | Smoking Room | All rooms are non smoking
|  | Interconnecting Rooms | 8
|  | Break up of Twin/King/Queen Beds | 12 twin bed rooms 68 king bed rooms
3 | GUEST CHECK INNS & WELCOME | Check in counters | 1
|  | No. of Check in staff | 2
|  | Check in time | 3:00 PM
|  | Check out time | 12:00 PM
|  | Check out counters | 1
|  | Welcome Drink | Non alcoholic drink
|  | Cold/Hot towels | NA
|  | Entertainment from Hotel - If Any | Rajasthani Singers
Can the host organise entertainment at the Lobby for guest arrival
|  | Do you have a seperate check in area for groups? | Yes
Process of Group Check in
|  | Hospitality Desk Location and Extension no: | Hotel main lobby. Extension no. #1226
|  | Welcome Amenities & Turndown amenities | Welcome Amenities : Whole fruits, Turndown: NA
4 | IN - ROOM AMENITIES | Welcome Amenities & Turndown amenities | Welcome Amenities : Whole fruits, Turndown: NA
|  | Fresh fruit platter | Yes
|  | Mini bar | Empty
|  | No of Water Bottles | 4 bottles of 500 ml complimentary
|  | Tea maker | Yes
|  | In room amenities/ toiletries | Bathroom amenities (2 robes, bathroom slippers,towels)
|  | Iron & Ironing board | Yes
|  | In house extra beds | 10
|  | Cloth Rack | None
|  | Full size Mirrors | Only in suites
|  | Safes In the Room | Yes inside the closet.
5 | F & B | Breakfast venue | The Dining Room
|  | Timings for Breakfast | 7:00 am to 10:30 am
|  | Room Service - is it 24 hours operational | Yes (limited menu for night)
|  | Do you have an All day dining restaurant | Yes
|  | Different Restaurants in the hotel | The Dining Room
Cusine & Capacity at the Restaurant
| BANQUET VENUES | Names of the Venue - Indoor and capacity to be advised | Ballroom
|  | Names of the Venue - Outdoor and capacity to be advised | Marwar Terrace, Outer Courtyard, Cresent Lawns, Guava garden,Croquet Lawns
Dos & Donts of each venue
|  | Time Restrictions on Music Indoor and Outdoor | Music outdoor till 10:30 PM only
|  | Baraat Procession Area | Poolside
|  | Can we have a small fire during the ceremony | Yes , outdoors
License required for each events
|  | Are drones allowed in your property | Yes with local authority permission
|  | Area Fire Works and Cold pyros permitted | Fireworks- Not permitted. Cold Pyros with Permission
|  | Do you have bartenders for banquet events | Yes
|  | Do you provide separate Kitchen space - incase if we get our own chefs (Indian) | No
|  | Venue for Hamper Packing | Kangan
|  | Office Control room - for event team | Hotel to advise
|  | Salon room for guests | Payal/Bindya
| CUISINES | What is the speciallity of the hotel
|  | Do you have Indian Chefs who can prepare Indian Food | Yes
|  | Sample menus to be shared | Done
|  | Beverage list to be shared | Done
|  | Can we get our own Alcohol | No
6 | OTHER FACILITIES AT THE HOTEL | Laundry & Ironing Services | On 15% discount
|  | Pool | Operational
|  | Gym | Operational
|  | Spa | On 15% discount
|  | Salon | Operational
|  | Shopping Store | NA
|  | ATM | NA
|  | In rooom dining | On 15% discount
Any Other
|  | Butler | 4 private and 4 floor butler
7 | ROOM RATE INCLUSiONS | Wifi | Complimentary
|  | Breakfast | Inclusive in room rate
|  | Triple Occupancy rate | Rs 8000 (plus taxes inclusive of breakfast)
|  | Guest Boat arrival departure transfers | Inclusive in room rate
|  | Extra Bed Pricing | Rs 8000 (plus taxes inclusive of breakfast)
8 | SPECIAL DISCOUNTS FOR THE GROUP | Food & Beverage - In room and Restaurant | On 15% discount
|  | Laundry & Ironing | On 15% discount
|  | Mini Bar | Empty
|  | Salon & Spa | On 15% discount
9 | TRANSPORT | Car Park space - How many cars can be parked | 2022-05-06
|  | Are Taxi's easily available on request? | Yes on chargeable basis
10 | OTHER IMPORTANT POINTERS | First Aid Kit at the hotel | Yes
|  | Doctor / Paramedics on premises | Yes on call
|  | Nearest Hospital | Aravali Hospital
|  | Nearest Super Market/Shopping Arcade | City Palace Entrance
|  | Venue for Guest Salon Set up | Bindya and Payal
|  | Venue for Hamper packing and Storage | Kangan
|  | Back office or internal meeting space for the EMC | Kangan
|  | Coordination with hotel team to place hampers and gifts (Please advise if the same is charged additonal?) | Complimentary
|  | Can guest/team order food from outside restaurant | No
|  | Terms & Conditions for set up to be shared | As advised by the hotel
|  | DOS & DONTS of the hotel for guests | As advised by the hotel
|  | SIGNAGE PLACEMENT POLICY | NA
11 | IMPORTANT EXTENSIONS | Hospitality | 1226
|  | Spa | 1228
|  | In-Room Service | Direct push button on boardline
|  | Laundry / Ironing | 0
|  | Front Desk | Direct push button on boardline
|  | Concierge | Direct push button on boardline
|  | Salon Extension | 1281
|  | Hotel Assistance | 0

## Table Requirement
Sr. No. | Elements | Qty | Venue | Date
Sr. No. | Elements | Qty | Venue | Date
A) | Lunch
1 | Console- 6 x 2.5 feet | 1 | Dinning Room | 28th October
2 | Photographer- 6 x 2.5 feet | 1 | Dinning Room | 28th October
B) | Family Performance
1 | Console- 6 x 2.5 feet | 1 | Inner Courtyard | 28th October
2 | Photographer- 6 x 2.5 feet | 2 | Inner Courtyard | 28th October
C) | After Party
1 | Console- 6 x 2.5 feet | 3 | Mewar Hall | 28th - 30th October
2 | Photographer- 6 x 2.5 feet | 2 | Mewar Hall | 28th - 30th October
D) | Cricket Match
1 | Console- 6 x 2.5 feet | 1 | Croquet Lawn | 28th & 29th October
2 | Photographer- 6 x 2.5 feet | 1 | Croquet Lawn | 28th & 29th October
E) | Sundowner Mehndi
1 | Console- 6 x 2.5 feet | 3 | Guvava Garden | 29th October
2 | Photographer- 6 x 2.5 feet | 2 | Guvava Garden | 29th October
F) | Safa Bandi
1 | Console- 6 x 2.5 feet | 1 | Pool Side | 30th October
2 | Photographer- 6 x 2.5 feet | 1 | Pool Side | 30th October
3 | Tables for safa - 6 x 2.5 feet | 2 | Pool Side | 30th October
4 | Tables for safa - 6 x 2.5 feet | 2 | Library Bar
G) | Baraat
1 | Console- 6 x 2.5 feet | 2 | Time Gate | 30th October
H) | Saloon
| Tables for saloon - 6 x 2.5 feet | 4 | TBD | 28th - 30th October
I) | Wedding Pheras
1 | Console- 6 x 2.5 feet | 2 | Outer Courtyard | 30th October
2 | Photographer- 6 x 2.5 feet | 2 | Outer Courtyard | 30th October

## Plug Point Requirement
Sr No | Date | Function | Venue | Plug Points For | Qty | Total
Sr No | Date | Event | Venue | Plug Points For | Qty | Total
1 | 28th October 2022 | Pool Gathering | Pool Side | Photo & Videographer | 2
|  |  |  | Wakie Talkie | 2
|  |  |  | Coolers | 2
2 | 28th October 2022 | Family Performance | Inner Courtyard | Photo & Videographer | 2
|  |  |  | Wakie Talkie | 2
3 | 28th October 2022 | After Party 1 | Mewar Hall | Photo & Videographer | 2
|  |  |  | Wakie Talkie | 2
|  |  |  | Bar | 2
|  |  |  | Anisa | 2
4 | 29th October 2022 | Circket Match | Croquet Lawn | Photo & Videographer | 2
|  |  |  | Wakie Talkie | 2
|  |  |  | Coolers | 6
5 | 29th October 2022 | Sundowner Mehndi | Guvava Garden | Photo & Videographer | 2
|  |  |  | Wakie Talkie | 2
|  |  |  | Cooler | 10
|  |  |  | Anisa | 2
|  |  |  | Bar | 2
6 | 29th October 2022 | After Party 2 | Mewar Hall | Photo & Videographer | 2
|  |  |  | Wakie Talkie | 2
|  |  |  | Bar | 2
7 | 30th October 2022 | Haldi | Inner Courtyard | Photo & Videographer | 2
|  |  |  | Wakie Talkie | 2
|  |  |  | Cooler | 4
8 | 30th October 2022 | Safa Bandi | Inner Courtyard | Photo & Videographer | 2
|  |  |  | Wakie Talkie | 2
|  |  |  | Cooler | 2
9 | 30th October 2022 | Baraat | Time Gate to croquet lawn | Photo & Videographer | 2
|  |  |  | Wakie Talkie | 2
|  |  |  | Cooler | 10
10 | 30th October 2022 | Wedding Ceremony | Rangmanch | Photo & Videographer | 2
|  |  |  | Wakie Talkie | 2
|  |  |  | Anisa | 4
|  |  |  | Coolers | 10
11 | 30th October 2022 | After Party 3 | Mewar Hall | Photo & Videographer | 2
|  |  |  | Wakie Talkie | 2
|  |  |  | Anisa | 2
|  |  |  | Bar | 2
Total